## Sheet1
Week	Start	End	Goal
1	01/28/19	02/03/19
2	02/04/19	02/10/19
3	02/11/19	02/17/19	project plan, user stories, screen mockups complete
4	02/18/19	02/24/19	database design and build: / - Users / - Batches / - Roles
5	02/25/19	03/03/19	Build Beans and DAO for entities (user, batch)
6	03/04/19	03/10/19	Build base servlets to feed JSPs / Convert to generic DAO
7	03/11/19	03/17/19	Deploy current build to AWS / Implement security roles / Implement index.jsp (sign in page) / Build LogIn.java servlet / LogOut.java servlet
8	03/18/19	03/24/19	-newBatch.jsp / -create new batch servlet
9	03/25/19	03/31/19	Get weather (need more information about this) / EditUser.java / EditUser.jsp
10	04/01/19	04/07/19	Build overview.jsp / DisplayOverview.java
11	04/08/19	04/14/19	editBatch.jsp / -edit batch servlet
12	04/15/19	04/21/19	mangeUser.jsp / ManageUsers.java
13	04/22/19	04/28/19
14	04/29/19	05/05/19
15	05/06/19	05/12/19
16	05/13/19

			add email notifications as a stretch goal
			Weather on the day the beer was brewed as well as bottled
			administrator reset a user password