## Sheet1
Week	Start	End	Goal
1	01/28/19	02/03/19
2	02/04/19	02/10/19
3	02/11/19	02/17/19	project plan, user stories, screen mockups complete
4	02/18/19	02/24/19	database design and build: / - Users / - Batches
5	02/25/19	03/03/19	Build Beans and DAO for entities (user, batch)
6	03/04/19	03/10/19	Build base servlets to feed JSPs / editUser / editBatch / DisplayOverview / Deploy current build to AWS
7	03/11/19	03/17/19	Build / -index.jsp / -new.jsp / -edit.jsp / Implement security
8	03/18/19	03/24/19	plumbing for index, new, and edit
9	03/25/19	03/31/19	Get and display weather information from API
10	04/01/19	04/07/19	More weather information from API
11	04/08/19	04/14/19	Build overview.jsp
12	04/15/19	04/21/19	Build: / -editUser.jsp / -editUser servlet
13	04/22/19	04/28/19	Implement security, build home page (index.jsp)
14	04/29/19	05/05/19
15	05/06/19	05/12/19
16	05/13/19

			add email notifications as a stretch goal
			Weather on the day the beer was brewed as well as bottled
			administrator reset a user password